## Sheet1
Online Poker Gantt Chart
CS 401-01 Project
Git Hub rep: https://github.com/jaybee707/PokerProj
TASKS/RESPONSIBILITES | Status of Task | People | Starting Date | Due Date | Total days to work on task | Summary of the Task
Update Documentation | Completed | Group | 2020-04-06 | 2020-04-10 | 5 | Update the files we received from the previous group. Any minor changes or updates we need to make to documentation, such as the gantt chart, will be added during this time.
Build Class Prototypes | Completed | Group | 2020-04-06 | 2020-04-10 | 5 | We will create all the necessary classes with prototype methods by this time. This gives us a better understanding of what's expected from each class.
Further discuss additions/changes for class prototypes | Working on it | Group | 2020-04-13 | 2020-04-19 | 7 | This is the time where we can look back at the prototypes we've created, and decide on whether or not we need to make additional changes.
Start testing/building network connectivity | Working on it | Group | 2020-04-13 | 2020-04-26 | 14 | This is the core of the game. We should preform basic network tests to ensure we can play the game with multiple users.
Work on finishing GUI and classes | Working on it | Group | 2020-04-13 | 2020-04-26 | 14 | This task is just work to be done towards finishing the project. The bulk of our project should be completed during this time.
Poker Tournament simulation | Working on it | Group | 2020-04-27 | 2020-05-03 | 7 | We should be able to run a basic simulation of our project at this point.
Finishing Touches: The project itself | Working on it | Group | 2020-04-27 | 2020-05-03 | 7 | Any additional changes needed should be finished during this time.
Ensure the project is complete | Working on it | Group | 2020-05-04 | 2020-05-11 | 7 | The project should be completed and ready for final project presentations. If we still need extra time for anything, this is the week to do it.